## Home
RFC Tracking Tool Example
Provided by ITSMTransition.com
Version 1.0

## RFC Tracking
Tracking Number | Status | CAB Review Date | Submission Date | Priority | Initiator of RFC | Short Description of Change | Reason for Change | Configuration Items | Customers and Users Impacted | Proposed Change Date | Proposed Change Time | Change Duration | Approved Change Date | Approved Change Time | Implementation Plan | Communication Plan | Post-Implementation Test Plan | Backout Plan | Comments | Result | Post Implementation Review | Status | Priority | Result
10001 | Submitted | 2013-06-27 | 2013-05-10 | Normal | Jeri Dugan | Implement new version of PayTraq | Annual Update | AppServer1, PayTraq | Payroll | 2013-07-04 | 18:00 | 30 Minutes | 2013-07-04 | 18:00 | 1. Stop web services on AppServer1 2. Make backup copy of PayTraq directory and contents 3. Install PayTraq 3.14a 4. Restart web services | Project manager will email Payroll manager about change on June 30, pending CAB approval | log into PayTraq, ensure new version number is displayed, and can view and edit timesheet. | 1. Delete PayTraq 3.14a 2. Rename PayTraq backup directory to production name 3. Restart web services |  |  |  | Submitted | Emergency | Successful
10002 | [21 empty] | Approved | Normal | Failed
10003 | [21 empty] | Rejected | Standard | Rolled Back
10004 | [21 empty] | Pending
10005
10006
10007
10008
10009
10010
10011
10012
10013
10014
10015
10016
10017
10018
10019
10020
10021
10022
10023
10024
10025
10026
10027
10028
10029
10030
10031
10032
10033
10034
10035
10036
10037
10038
10039
10040
10041
10042
10043
10044
10045
10046
10047
10048
10049
10050
10051
10052
10053
10054
10055
10056
10057
10058
10059
10060
10061
10062
10063
10064
10065
10066
10067
10068
10069
10070
10071
10072
10073
10074
10075
10076
10077
10078
10079
10080
10081
10082
10083
10084
10085
10086
10087
10088
10089
10090
10091
10092
10093
10094
10095
10096
10097
10098
10099

## Field Descriptions
Red Fields | Are managed by the Change Manager/CAB
Green Fields | Are entered by Change Initiators
Field | Description/Instructions | Comments
Tracking Number | Unique ID number assigned by CM/CAB
Status | Current status of request. Field Managed by CM/CAB Submitted - RFC has been accepted by CM/CAB for consideration Approved - RFC has been reviewed and approved by CM/CAB Rejected - RFC has been reviewed and rejected by CM/CAB - explanation provided in Comments field Pending - RFC has been reviewed and is awaiting further information, explanation or other input. Explanation provided in Comments field.
Priority | Priority of RFC: Normal - Normal changes Standard - Standard, pre-approved change Emergency - Changes that must happen faster than normal CAB schedule allows. Typically associated with either rapidly emerging business needs or Incident Management
Initiator of RFC | Name of the person initiating RFC
Submission Date | Date the RFC is submitted
Short Description of Change | Description of the change being requested
Reason for Change | Description of why the change is being requested. Should explain the expected results and and benefits from the business perspective. For significant changes, this can be a pointer to a more complete plan
Configuration Items | List all Configuration Items impacted by the change. | Configuration Items are components of the IT infrastructure, both hardware and software that managed by the IT organization
Customers and Users Impacted | What Customers and Users are impacted by the proposed change
Proposed Change Date | Desired implementation date of proposed change
Proposed Change Time | Desired time to implement change
Change Duration | Estimated time to fully implement change, including time to fully roll back if needed
Approved Change Date | Date for which CM/CAB approves change | If organization has established Release Windows, substitute to match.
Approved Change Time | Time for which CM/CAB approves change
Implementation Plan | Detailed plan to implement proposed change. Describes the major steps to performed. Should include who will be performing the steps. For large, or high impact changes, may be a pointer to Release or project plans. | The level of detail depends on the culture as well as the nature of the requested change. Encourage requestors to error on the side of more detail.
Communication Plan | What information will be communicated to customers, who, and how will the information be communicated.
Post-Implementation Test Plan | How will the change be tested once complete to ensure the desired outcomes will be realized by the business | If organization has Customer Acceptance Plans, include here.
Backout Plan | Detailed plan to undo (backout) the change in the event of trouble or unintended results. For large or high impact changes, may be a pointer to Release or project plans.
Comments | Additional information as needed - use to document "Pending" or "Rejected" requests
Result | Status indicating the result of the change: Success - Change worked as planned Failed - Change failed, customer impacted Rolled Back - Change failed, rolled back without customer impact
Post Implementation Review | Comments on CAB's review of the change. Include any lessons learned or opportunities for improvement

## Definition of Terms
Term | Description
Change Manager (CM) | Change Manager is responsible for facilitating the Change Management process, Chair CAB meetings, and is ultimately responsible for approving changes
Change Advisory Board (CAB) | Board tasked with reviewing Requests for Change to assess risk of adverse business impact of proposed changes. Team is composed of representatives from all IT functions (Service Desk, DBA, Network, Development, Etc), and decision makers - IT managers. Change Manager may invite business representatives and guests with specialized skill set useful in evaluating a particular change
Request for Change (RFC) | Formal request to make a change.
Change Initiator | Person requesting the change. Initiator must attend CAB to represent the change and answer any questions or concerns raised by CAB
Change Implementers | Staff who will be carrying out the work described